## About
ABOUT THIS GANTT CHART
Visualize and track your projects using this Gantt chart template. To start, enter the tasks you're working on in the milestone description section and then enter details for each task. The data will automatically update and it’s easy to insert new tasks or use the scrollbar to scroll through the timeline.
• Use the progress column to add how much of the project you finished by adding a percentage number • Add the day you started your project in the start date column • Finish your calculations by filling in the number of days you need to complete your project in the days column

## Roadmap
t
PROJECT: Analysis of Earning-Related Factors Impact on Stock Prices for VP Analytics
| (Team name) |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
| Project start date: | 2026-01-18 |  |  |  |  | 1月 | [13 empty] | 2月 | [27 empty] | 3月
| Scrolling increment: | 4 | time axis 2026-01-19 to 2026-03-15
| Task Description | Details | Assigned to | Progress | Start Date | Starts on Day | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
| Phase 0: Complete Project Plan + Roadmap, Project Charter | -Project Plan: Include problem statement and business questions, and this Project Roadmap (in Appendix) -Submit Project Charter | All | 25% | 2026-01-18 | 0 | bar: M to S
| Phase 1: Data Sourcing, Preparation, and Initial Exploration | -Find relevant data from public sources -Extract and clean the data -Initial exploratory analysis & formulate hypotheses | All | 0% | 2026-01-25 | 7 | bar: M to S
| Phase 2: Focused Analysis | -Team 1 will analyse pre-earnings drift, announcement-day reactions, and post-earnings price and volatility behaviour. -Team 2 will examine how different earnings outcomes and financial profiles relate to observed market reactions. -Team 3 will evaluate whether earnings behaviour changes across macroeconomic regimes, both interest rates and inflation. | All | 0% | 2026-02-01 | 14 | bar: M to S
| Phase 3: Holistic Analysis | -Results from all focus areas will be combined to examine interrelated effects. -Simple back-testing techniques will assess whether identified patterns are consistent across multiple earnings cycles and market conditions. | All | 0% | 2026-02-01 | 14 | bar: M to S
| Stage 4: Strategic & Inferential Conclusions | -Findings will be collated into strategic insights and presented through clear visualisations, a final report, and a reusable Python analysis framework. | All | 0% | 2026-02-08 | 21 | bar: M to S
| 4A: Prepare (first) presentation materials | -Decide on key messages and structure for Employer Partner Initial Recommendation Presentation -Prepare materials for EP Initial Recommendation Presentation | All | 0% | 2026-02-08 | 21 | bar: M to S
| 4B: Deliver first presentation, prepare for second presentation | -Prepare for and deliver Employer Partner Initial Recommendation Presentation (due Feb 23, 13:00 UK time) -Decide on key messages and structure for Employer Partner Final Presentation | All | 0% | 2026-02-15 | 28 | bar: M to S
| 4C: Deliver second presentation, prepare group report | -Prepare for and deliver Employer Partner Final Presentation (due Mar 2, 13:00 UK time) -Prepare Final Report (due 3/2, 13:00 UK time) | All | 0% | 2026-02-22 | 35 | bar: M to S
| 4D: Prepare individual report | -Prepare and submit individual reports (due Mar 5, 13:00 UK time) | All | 0% | 2026-02-22 | 35 | bar: M to W
To add more data, Insert new rows ABOVE this one
Formulas:
Start Date = C6+[Legend:]